## Slide 1: Division 10 Stallings Projects
Lee Ainsworth, P.E.
August 11, 2025
Copy/paste any of the icons below into your presentation. Please change color to white if using them on a dark background.

## Slide 2: Agenda
Projects
  In Development
    U-4714 AC – Old Monroe Road Widening
    U-4714 BA/BB – Old Monroe Road Widening
    U-6170 – Lawyers Road Widening (PE Only)
  Under Construction
    U-5112 - Pleasant Plains at Potter Intersection
    U-5808 - Chestnut Lane Extension
    I-5507 - I-485 Express Lanes
    U-4713 A - Mckee Road Extension
  Not funded
    U-4913B – Idlewild Road Interchange
Other slide variations are available. Select Insert above and choose “new slide” to see all the options.

## Slide 3: U-4714 AC – Old Monroe Road

## Slide 4: U- 4714 AC Old Monroe Road Widening
Funded Project Scope:
  Widen Old Monroe Road to Four Lanes from east I-485 to Morningside Meadow Lane.
Important Dates:
  Contract Award in Summer 2026
  Construction Estimate $45.2M
Current Status:
  Utility Relocation Underway
Other slide variations are available. Select Insert above and choose “new slide” to see all the options.

## Slide 5: U-4714 BA/BB – Old Monroe

## Slide 6: U-4714 BA/BB – Old Monroe Road Widening
Funded Project Scope:
  U-4714 BA - Widen Old Monroe Road to Four Lanes from Morningside Meadow Lane to Indian Trail Road
  U-4714 BB – Widen Old Monroe Road to Four Lanes from Indian Trail Road to East of Wesley Chapel Stouts Road
Important Dates:
  Contract Award
    U-4714 BA – Summer 2026
    U-4714 BB – Winter/Spring 2028
  Construction Costs
    U-4714 BA – Est. $22.6M
    U-4714 BB – Est. $77.8M
Current Status:
  U-4714 BA – Utility Relocation Underway
  U-4714 BB – ROW Acquisition Underway
Other slide variations are available. Select Insert above and choose “new slide” to see all the options.

## Slide 7: U-6170 – Lawyers Road Widening (PE Only)

## Slide 8: U-6170 Lawyer Road Widening
Funded Project Scope:
  Widen Lawyers Road to Four Lanes from I-485 to Stevens Mill Road
Current Status:
  Project is currently funded for preliminary engineering only.
  In beginning stages of development with forecast and capacity analysis complete.
Other slide variations are available. Select Insert above and choose “new slide” to see all the options.

## Slide 9: U-5112 - Potter Road Intersection

## Slide 10: U-5112 Potter Rd Intersection Improvements
Funded Project Scope:
  Construct intersection improvements including left turn lanes and modification of traffic signal.
Important Dates:
  Contract was awarded in April 2024
  Current anticipated completion in November 2026
Current Status:
  Under Construction(Est. $10.9M)
Other slide variations are available. Select Insert above and choose “new slide” to see all the options.

## Slide 11: U-5808 - Chestnut Lane Extension

## Slide 12: U-5808 Chestnut Lane Extension
Funded Project Scope:
  Construct new four-lane roadway from Matthews Indian Trail Road to Gribble Road
Important Dates:
  Contract was awarded in January 2024
  Current anticipated completion in February 2027
Current Status:
  Under Construction(Est. $20.5M)
Other slide variations are available. Select Insert above and choose “new slide” to see all the options.

## Slide 13: I-5507 - I-485 Express Lanes

## Slide 14: I-5507 I-485 Express Lanes
Funded Project Scope:
  Construct one express lane in each direction from I-77 to US 74
Important Dates:
  Contract was awarded in October 2018
  Current anticipated substantial completion in December 2025
Current Status:
  Under Construction(Est. $346M)
Other slide variations are available. Select Insert above and choose “new slide” to see all the options.

## Slide 15: U-4713A - Mckee Road Extension

## Slide 16: U-4713A Mckee Road Extension
Funded Project Scope:
  Construct new two-lane roadway from Pleasant Plains Road to East John Street
Important Dates:
  Contract was awarded in October 2024
  Current anticipated completion in March 2027
Current Status:
  Under Construction(Est. $13.5M)
Other slide variations are available. Select Insert above and choose “new slide” to see all the options.

## Slide 17: U-4913B – Idlewild Road Interchange

## Slide 18: U-4913B Idlewild Road Widening (Not funded)
Project Scope:
  Widen Idlewild Road to six lanes from I-485 to Stevens Mill Road
Current Status:
  Project is currently not funded for any development phase
Weddington Update
Other slide variations are available. Select Insert above and choose “new slide” to see all the options.

## Slide 19
Lee Ainsworth, PE
clainsworth@ncdot.gov
704-983-4400
Other slide variations are available. Select Insert above and choose “new slide” to see all the options.